# Qiyuan T1 Robot — Project Execution Guide & 11-Day Plan

Based on: "Qiyuan T1 Robot — Complete Secondary Development & SDK Engineering Guide" v1.0 (verified 2026-10-06)
Target baseline: Ubuntu 22.04.x + ROS 2 Humble + Fast DDS (rmw_fastrtps_cpp) + aimdk_msgs 1.0.0
Prepared: 2026-10-08 | Plan window: 2026-10-09 to 2026-10-19 (11 days) | Revision 2 (2026-10-08)
Project repository: https://github.com/Shawon986/Qiyuan-T1-Robot-Project

# 0. Project Definition (confirmed 2026-10-08)

Application-layer development ONLY — no hardware or firmware modification (warranty intact). The robot is an "entry terminal": our Python app runs on top of the official Qiyuan SDK and combines the built-in capabilities into four demo features, plus cloud integration.

| Feature | Pipeline | Building blocks (SDK + cloud) |
| --- | --- | --- |
| Cantonese conversation | wake word 机器人 → ASR → Qwen LLM → TTS → speaker | SDK mic/audio record + audio playback; iFlytek Cantonese ASR + TTS (cloud); Qwen LLM with in-session long-context memory; robot /aima/agent/asr_result as optional wake trigger |
| Follow-and-film | voice command → vision lock → gimbal track → video record | SDK camera (CaptureJpegImage / RTSP) + MC upper-body/gimbal command (resource IDs from PrimeBot) + app-side video encode (OpenCV) |
| Dancing | JSON timeline → music / chassis / gimbal / lights / screen synchronized | SDK preset motions + locomotion velocity + LED strip + screen/expression + music playback (media_role=Music) |
| SeeDance integration | record video + voice prompt → upload Volcano TOS → SeeDance AI video task → web status → result back to robot | tos SDK (Volcano) + SeeDance REST API (spec from user) + robot audio/screen for result delivery |

Safety posture: MC high-level interfaces only; preset motions for choreography; never low-level joint control (warranty + handbook requirement).

# 1. Project Snapshot

| Item | Published value | Notes |
| --- | --- | --- |
| Robot | Qiyuan / PRIMEBOT T1 | Transformable quadruped/bipedal robot; T1 vs T1 Pro must be confirmed for your unit. |
| SDK repository | https://gitcode.com/primebot/t1-sdk.git | Official GitCode repo, label v0.9.4.7. |
| Pinned SDK commit | fe2e186c867391ec78b301accdc91f0260ad0ff3 | Anchor ALL source work to this SHA (checkout before building). |
| Developer portal SDK card | v1.0.0.0 | Not proven equivalent to the repository revision — treat separately. |
| ROS interface package | aimdk_msgs 1.0.0 | Package/schema version only — NOT a firmware or global API version. |
| Default LAN | MC board 10.1.1.100, brain board 10.1.1.101, PC 10.1.1.99/24 | Factory defaults; always confirm actual addresses. |
| Wired vs Wi-Fi | Wired is the engineering baseline | Wi-Fi AP: T1-<last 10 of SN>, random password per robot (board-side file). |

# 2. Accounts, Credentials, Activation & API Keys (do these FIRST)

Important truth from the handbook: the T1 SDK itself requires NO API key. The only mandatory credentials are robot SSH access, which is issued privately by PrimeBot after-sales support — never published, never guessable.

| Item | What to do | Where / who | Time needed |
| --- | --- | --- | --- |
| PRIMEBOT developer portal account | Register an account; use it to track SDK cards, manuals and announcements. | www.primebot.cn developer portal | Day 1 — immediate |
| GitCode account | Register (free). Cloning the public repo may work without it, but an account lets you watch issues/releases. | gitcode.com | Day 1 — immediate |
| Robot SSH credentials | REQUEST from after-sales support. Account form is ssh run@<board-IP>. Credentials are per-unit and confidential. | PrimeBot after-sales support / robot owner | Day 1 — may take days, request early |
| Wi-Fi AP password (optional) | Generated randomly at first boot, stored board-side. Obtain from owner/support if Wi-Fi debugging is needed. | Robot owner / PrimeBot | Only if needed |
| Robot Developer Mode activation | Authorized operator runs yamo mode edit on the motion-control board: select develop → basic, then reboot/power-cycle the robot. | SSH session on the robot (Section 6) | Day 5 — needs SSH credentials + physical access |
| API keys for AI features (OPTIONAL) | The SDK needs none. Only if you build the AI agent: choose your own LLM / ASR / VLM / weather provider (no vendor-endorsed provider exists). Store keys in env vars or a secret manager — never in code, logs or shell history. | Provider of your choice | Day 9 — only for AI features |
| iFlytek open platform (Cantonese ASR + TTS) | Register, create an app, obtain APPID / APIKey / APISecret. Enables the Cantonese conversation feature. | aiui.xfyun.cn | Needed for Days 6–7 |
| Qwen / DashScope API key | Alibaba Model Studio API key; use qwen-long for the in-session long-context memory. | bailian.console.aliyun.com | Needed for Day 6 |
| Volcano TOS credentials | AccessKey + SecretKey + bucket + endpoint for video storage before SeeDance submission. | console.volcengine.com | Needed for Day 9 |
| SeeDance platform API spec | REST endpoints for task submission / status query / result delivery + auth. | Your own platform | Needed for Day 9 |

# 3. Environment Setup — Current Status (updated 2026-10-08)

| Checklist item | Status | Detail |
| --- | --- | --- |
| Ubuntu 22.04.x | DONE | WSL2 (Windows 11) distro Ubuntu-22.04. Note: handbook says macOS/Windows are unsupported — WSL Ubuntu 22.04 satisfies the Linux baseline; robot connectivity uses the USB-NIC plan in Section 5. |
| ROS 2 Humble | DONE | ros-humble-desktop + ros-dev-tools installed and verified (ros2 doctor 5/5, talker node ran). |
| Locale / apt mirroring | DONE | en_US.UTF-8; ROS apt + rosdep + pip use TUNA/USTC mirrors (network blocks GitHub/packages.ros.org). |
| SDK build dependencies | DONE (Day 2) | colcon full set, rosidl generators/runtime, cmake/g++, FFmpeg/GStreamer, nanobind/numpy/opencv. |
| UDP socket buffers | DONE (Day 2) | 24 MiB host maxima (/etc/sysctl.d/99-primebot-sdk.conf). |
| T1 SDK clone + build | DONE (Day 3) | Pinned commit fe2e186…; colcon build: 4 packages, 0 errors (9 min 41 s); 53 aimdk_msgs interfaces verified; Fast DDS profile env verified. |
| Wired robot network | TODO — Day 4 | Static 10.1.1.99/24 on the wired NIC; USB-Ethernet adapter via usbipd (Section 5). |
| Developer Mode on robot | TODO — Day 5 | yamo mode edit → develop → basic → reboot (authorized operator). |

# 4. Installation Steps (exact vendor commands from handbook Chapter 4)

## 4.1 SDK build dependencies (required) — DONE 2026-10-08

sudo apt update && sudo apt install -y python3-colcon-common-extensions python3-dev python3-pip ros-humble-rosidl-default-generators ros-humble-rosidl-default-runtime

Verify: colcon version-check

## 4.2 C++ / vision / Python dependencies (for camera + Ruckig examples) — DONE

sudo apt install -y cmake build-essential pkg-config libavcodec-dev libavformat-dev libavutil-dev libswscale-dev libgstreamer1.0-dev libgstreamer-plugins-base1.0-dev libyaml-cpp-dev

python3 -m pip install --user nanobind numpy opencv-python

Verify: python3 -c 'import nanobind, numpy, cv2'

## 4.3 Clone the pinned SDK (English-only path, NO spaces/Chinese chars) — DONE

mkdir -p "$HOME/t1_workspaces" && cd "$HOME/t1_workspaces"

git clone https://gitcode.com/primebot/t1-sdk.git primebot_sdk

cd primebot_sdk && git checkout fe2e186c867391ec78b301accdc91f0260ad0ff3

git rev-parse HEAD   # must print fe2e186c867391ec78b301accdc91f0260ad0ff3

## 4.4 Build and source the SDK overlay — DONE (4 packages, 9 min 41 s)

source /opt/ros/humble/setup.bash

colcon build --cmake-args -DCMAKE_BUILD_TYPE=Release

source "$PWD/install/setup.bash"

Verified: ros2 interface show aimdk_msgs/msg/Bms + srv/PlayTts; RMW_IMPLEMENTATION=rmw_fastrtps_cpp; profile vars → install/aimdk_msgs/share/aimdk_msgs/config/fastdds_profiles.xml; 53 interfaces.

## 4.5 Host UDP buffer limits (vendor: 24 MiB maxima for the 20 MiB profile) — DONE

sudo tee /etc/sysctl.d/99-primebot-sdk.conf >/dev/null <<'EOF'
net.core.rmem_max = 25165824
net.core.wmem_max = 25165824
EOF

sudo sysctl --system && sysctl net.core.rmem_max net.core.wmem_max

# 5. Network Setup (handbook Chapter 3 — WSL-adapted, Rev 2)

Baseline: Use a WIRED connection. Wi-Fi is for temporary debugging only; never send control over wired and wireless simultaneously.

Disable unrelated Wi-Fi/hotspot adapters during robot sessions — extra NICs break DDS discovery.

WSL networking decision (2026-10-08): mirrored mode was tested and is UNSTABLE with the local proxy/VPN driver (WSL error 0x8007054f, falls back to no network). NAT mode is used by default.

For the robot LAN, Plan B: pass a USB-Ethernet adapter into WSL with usbipd-win — on Windows: usbipd list / usbipd bind --busid <BUSID> / usbipd attach --wsl; the adapter then appears as a real Linux NIC (e.g. eth1) inside WSL. (Alternative: retry mirrored mode with the proxy software fully off.)

Identify the wired interface (predictable name, not guessed):

ip -br link && ip -br addr

Set the documented static address on the wired profile (replace <PROFILE> with the real nmcli name):

sudo nmcli connection modify '<WIRED_CONNECTION_NAME>' ipv4.method manual ipv4.addresses 10.1.1.99/24 ipv4.gateway '' ipv4.dns ''

sudo nmcli connection up '<WIRED_CONNECTION_NAME>'

Reachability checks (use CONFIRMED board IPs — defaults are 10.1.1.100 / 10.1.1.101):

ping -c 3 10.1.1.100 && ping -c 3 10.1.1.101 && ip route get 10.1.1.100

SSH to the motion-control board once credentials arrive:

ssh run@<MOTION_CONTROL_BOARD_IP>

Note: no default DNS/gateway is documented for the direct link — do not add routes or DNS "just in case".

# 6. Robot Developer Mode Activation (handbook Chapter 5)

The robot ships in Standard production mode where ROS nodes are not discoverable. An AUTHORIZED OPERATOR must switch to Develop mode and reboot the robot before any ROS 2 communication works.

Preconditions: robot stationary, controlled test area, emergency power-off procedure known, isolated wired LAN, personnel separation.

Activation steps:

ssh run@<MOTION_CONTROL_BOARD_IP>

yamo mode edit

In the interactive menu select develop, confirm; then select basic, confirm. The board reports success and that a restart is required.

Perform the vendor-approved robot reboot / power-cycle (a physical step — never automated).

Verify afterwards (in a shell with ROS + SDK sourced):

ros2 node list && ros2 topic list -t && ros2 service list -t

Expected examples: nodes /hal_camera, /hal_audio, /mc_ros2_node; /aima/hal/... and /aima/mc/... topics; /aimdk_5Fmsgs/srv/... services.

Return to production: yamo mode edit → standard → reboot (part of test closure).

Safety: Develop+Basic is the normal starting point. Advanced / low-level joint control (domains.mc.low_level_dev) requires a dedicated physical test plan and PrimeBot confirmation.

# 7. First-Day Success Checklist (condensed from handbook)

| # | Step | Pass condition |
| --- | --- | --- |
| 1 | Identify & secure | Asset/serial recorded; controlled area; emergency procedure approved. |
| 2 | Confirm compatibility | Firmware ↔ SDK mapping confirmed with PrimeBot (repo v0.9.4.7 / portal v1.0.0.0 / aimdk_msgs 1.0.0 are NOT interchangeable). |
| 3 | Workstation | lsb_release -d → Ubuntu 22.04; source /opt/ros/humble/setup.bash; echo $ROS_DISTRO → humble. |
| 4 | Obtain source | git checkout fe2e186…; git rev-parse HEAD matches. |
| 5 | Build | colcon build --cmake-args -DCMAKE_BUILD_TYPE=Release finishes cleanly. |
| 6 | Source & inspect | ros2 interface show aimdk_msgs/msg/Bms prints the schema. |
| 7 | Wired LAN | ip -br link/addr correct; route via intended NIC (USB NIC in WSL). |
| 8 | Reachability | ping OK to both confirmed board IPs. |
| 9 | Developer mode | yamo mode edit → Develop+Basic accepted; robot rebooted. |
| 10 | Environment | ROS_DOMAIN_ID, RMW_IMPLEMENTATION, both Fast DDS profile vars recorded. |
| 11 | Discover graph | ros2 node/topic/service list show the target graph. |
| 12 | Read telemetry | ros2 topic info -v /aima/hal/bms/state; echo --once returns a message. |
| 13 | First app | Read-only monitor built and running; no motion commands. |
| 14 | Save evidence | Asset, firmware, SHA, OS, IPs, domain, profile, graph types/QoS logged. |

# 8. The 11-Day Plan (Oct 9 – Oct 19, 2026)

Days 2–3 were completed ahead of schedule on 2026-10-08 (environment + SDK build & verification). Day 6 software was also pre-completed on 2026-10-08: t1_monitor app (BMS/touch/ASR + guarded TTS, fail-closed) built against the portal SDK v1.0.0.0 overlay and offline-tested (6/6); first_contact.sh and net_bringup.sh scripts are in the repo. Remaining days as planned; weekend days used for work needing no after-sales replies.

| Day | Date | Focus | Concrete tasks | Success criteria |
| --- | --- | --- | --- | --- |
| 1 | Fri Oct 9 | Accounts & credentials | Register PRIMEBOT developer portal + GitCode accounts. Contact PrimeBot after-sales for board SSH credentials and firmware↔SDK compatibility confirmation. Read handbook Ch. 1–5. | Accounts live; credentials request submitted with your asset serial number. |
| 2 | Sat Oct 10 | Environment completion ✔ DONE 2026-10-08 | SDK build deps, pip packages, UDP buffers. Networking: NAT default; usbipd USB-NIC plan for robot LAN. | All deps verified; rmem_max/wmem_max = 25165824. |
| 3 | Sun Oct 11 | SDK build ✔ DONE 2026-10-08 | Clone t1-sdk, checkout fe2e186…, colcon build Release, source overlay. Verify interfaces + Fast DDS env vars. | 4 packages built; 53 interfaces; RMW=rmw_fastrtps_cpp; profile paths correct. |
| 4 | Mon Oct 12 | Network bring-up | USB-Ethernet adapter via usbipd-win; set 10.1.1.99/24 on it; ping 10.1.1.100/.101; record ACTUAL IPs; disable Wi-Fi during tests. | Both boards reply to ping via the wired NIC. |
| 5 | Tue Oct 13 | Developer Mode activation | Authorized operator: ssh run@<MC-IP>, yamo mode edit → develop → basic, robot reboot. Run graph discovery; record domain/QoS/types. | ros2 node/topic/service list show the real graph (/hal_camera, /mc_ros2_node, …). |
| 6 | Wed Oct 14 | Cantonese conversation pipeline | Build conversation app: iFlytek Cantonese ASR + TTS adapters, Qwen long-context memory, wake word 机器人. Test fully on PC (mic/speaker on Windows/WSL). Robot-side: live telemetry + audio device inventory. | PC end-to-end Cantonese chat works; robot BMS/touch telemetry live via t1_monitor. |
| 7 | Thu Oct 15 | Follow-and-film (vision + gimbal) | Person detection (OpenCV/YOLO) + tracking loop; gimbal control via MC upper-body command with PrimeBot-confirmed resource IDs; app-side video encode. PC test with webcam; robot gimbal test with operator. | Vision locks target on PC; gimbal responds to proportional commands on robot (supervised). |
| 8 | Fri Oct 16 | Dancing (JSON timeline) | Timeline executor: music + preset motions + locomotion velocity + LED + screen synchronized. Dry-run offline with simulated timeline; supervised robot run with safe presets only. | A 30-60 s choreography runs synchronized on the robot (preset motions only). |
| 9 | Sat Oct 17 | SeeDance integration | Volcano TOS uploader + SeeDance REST client + task status polling + result delivery to robot. Test with a sample video end-to-end (no robot needed for the cloud path). | Sample video uploaded → SeeDance task completes → result retrieved. |
| 10 | Sun Oct 18 | Full integration & evidence | All four features on the robot: conversation, follow-and-film, dance, SeeDance flow. Timeouts, fail-closed checks, evidence pack (SHA, firmware, IPs, domain, QoS, logs). | All four demos work end-to-end on the robot with fail-closed behavior. |
| 11 | Mon Oct 19 | Review & handover | Safety review before any further motion work. Deployment decision (PC vs board). Autostart only via vendor process manager. Final report + demo. | Deployment recorded; demo delivered; next-phase plan written. |

# 9. Non-Negotiable Safety Rules

Inspect before you invoke: never "test connectivity" with motion commands (SetMc*, velocity, servo, shutdown).

Low-level joint control bypasses protections — separate physical plan, safety officer, tethered/fixtured robot, PrimeBot confirmation.

Developer mode exposes interfaces: closed trusted LAN only, never public internet.

Never store passwords or API keys in code, logs, shell history, or bag metadata.

Do not fabricate facts the handbook marks "Not publicly documented / Requires confirmation from PrimeBot" — ask support instead.

Keep the SDK clone unmodified; develop in sibling packages and record the base SHA in every test log.

# 10. Command Cheat Sheet

| Purpose | Command |
| --- | --- |
| Enter ROS shell | source /opt/ros/humble/setup.bash && source ~/t1_workspaces/primebot_sdk/install/setup.bash |
| Verify underlay | lsb_release -d && echo $ROS_DISTRO |
| Verify SDK interfaces | ros2 interface show aimdk_msgs/msg/Bms ¦ ros2 interface show aimdk_msgs/srv/PlayTts |
| DDS environment | printenv ROS_DOMAIN_ID RMW_IMPLEMENTATION FASTRTPS_DEFAULT_PROFILES_FILE FASTDDS_DEFAULT_PROFILES_FILE |
| Graph discovery | ros2 node list ¦ ros2 topic list -t ¦ ros2 service list -t |
| BMS read (safe) | timeout 5 ros2 topic echo /aima/hal/bms/state --once |
| Topic details | ros2 topic info -v /aima/hal/bms/state |
| Activate developer mode | ssh run@<MC-IP> → yamo mode edit → develop → basic → reboot robot |
| Return to production | yamo mode edit → standard → reboot robot |
| UDP buffers | sysctl net.core.rmem_max net.core.wmem_max (expect 25165824) |

Reference: the full handbook (Qiyuan_T1_Complete_Engineering_Guide.docx) remains the authoritative source; this plan is an execution summary. Version discipline: repo v0.9.4.7, portal v1.0.0.0, aimdk_msgs 1.0.0 — never treat them as interchangeable.